## Sheet1
Week beginning: 05/11/12 Task Sheet completed by:
Task # | Task Name | Task Description | Assigned To | Est hours | Actual Hours | Completed (Y/N) | Signed Off
1 | Database | Create tables for: - Customer - Accommodation | Scott/Sarah | 2
2 | Prototype | Add new customer interface - Name and address | Nikolay | 2
3 | Prototype | Search for customer - Search by customer name | Nikolay | 2
4 | Prototype | Search for accomodation (no need to add for now as they will be added manually to database) - Search for accomodation by name/type | Nikolay | 2
5 | Test cases | Design tests for: - Add new customer - Search for accommodation by name/type | Nick | 2

## Sheet2
Week Beginning: 05/11/12 Minutes taken by: Sarah
Area of Discussion | Discussion
Client Meeting 5/11/12 | Clarifying areas raised in last group meeting (see Meeting Plan/ recording). Suggestion made that calendar is for bookings for the following week only. On-screen narrative 'nice to have' not essential. Name and address should be entered as soon as possible to allow for sending emails/promo material. Is an account is closed, a corresponding status should be given, but details remain on the system. If a customer wants to cancel a booking, perhaps a cancellation fee should be charged. Confirmation of bookings/cancellations should be on-screen only, to be relayed to the customer. Feedback should be based on a rating scale similar to trip advisor i.e. customer leaveing feedback based on stay. Customer unsure as to how the call log should function User guide on-screen or manual TBC The program can be/should be installed on local machine
Group Discussion 5/11/12 | Scott and Sarah to design prototype database Nikolay to implement prototype system Nick to build test cases and prioritise user stories Scott and Sarah to break down tasks to user stories