## Sheet1
Week beginning: Task Sheet completed by:
Task # | Task Name | Task Description | Assigned To | Est hours | Actual Hours | Completed (Y/N) | Signed Off
1 | User stories | Create user stories for all tasks | Group | 2 | 2 | Y
2 | Task sheet | Design task sheet template and implenement for current week | Sarah | 1 | 1 | Y
3 | Minutes | Design minutes sheet and implement for current week | Sarah | 1 | 1 | Y
4 | Mind maps | Create mind maps for overall project and each user story | Sarah/Scott | 2
5 | Meeting plan | Design template for meeting plans and implement for forthcoming meeting between developers and client | Sarah | 1
6 | Requirements | Lay out a basic requirment schedule to be disussed in the meeting |  | 2

## Sheet2
Week Beginning: 29/10/12 Minutes taken by: Sarah
Area of Discussion | Discussion
Prototype | Nikolay expressed that he'd like to produce a prototype fairly early on in this iteration. The benefit will be that it can be shown to the customer to verify that it is what's required.
Requirements | User story boards have been created for the first two topics (customer account management and accommodation related requests)
Clarification | Several questions arose regarding clarification of requirements: 1. Does closing a customer account also require removal of all corresponding data or is the account simply deactivated? 2. Is an on-screen script/narrative used in the main system? 3. What size area does the information centre deal with? (Town/city/county etc) 4. Should the confirmation only be displayed on the screen or should an email or other correspondance be sent to the customer? 5. Cancellations context - does this mean cancel a customer's booking or check for last minute cancellations? 6. At which point should a new customer be created, at the start of a new call or only if they wish to book? 7. Should the feedback be given by the customer based on experience, or be given to the customer by the tourist info center? 8. Is this purely for audit (uneditable) or just a notes section?
Assumptions | 1. The system is stand-alone 2. The demo needs to run from a CD 3. A user guide is needed 4. An interface will be required 5. A back-end storage system will be required 6. There is only 1 user group (potential employees)